## Sheet1
|  |  | Key Project Assumptions / Details: The application will be connected to the sample database. Packages will be imported to view tables that are present in both the packages and the database.. Tables can be searched individually from the entire sample database | [25 empty] | Date |  |  | 2021-10-07
Project Name: Data Visualization Capstone Proposal # 1 | [28 empty] | Revision
| Major Tasks |  | Project Completed By:
1 | Configuring Sample Oracle Database Locally |  |  |  | X | [23 empty] | X | X | X
2 | Setup Version Control (ex. Github) |  |  |  | X | [25 empty] | X
3 | Connect to and Query the Sample Database via program |  |  |  |  | X | [22 empty] | X | X | X
4 | Functionality to determine links for a specified table | [5 empty] | X | [21 empty] | X
5 | UI skeleton with placeholders for input elements | [5 empty] | X | [23 empty] | X
6 | Functionality to import pl/sql packages | [6 empty] | X | [21 empty] | X
7 | Functionality to parse a package for table links | [6 empty] | X | [21 empty] | X
8 | Output table links initially in textual format | [7 empty] | X | [19 empty] | X
9 | Exception Handling | [8 empty] | X | [18 empty] | X | X | X
10 | Coverting textual links into UI elements | [9 empty] | X | [19 empty] | X
11 | Display table links within the UI | [10 empty] | X | [18 empty] | X
12 | Saving/Exporting table link visuals | [10 empty] | X | [16 empty] | X | X | X
13 | Final Debugging | [11 empty] | X | [15 empty] | X | X | X
User Specifies number of table links to view
Scaling/Zoom feature for display window
Multiple display windows for loaded packages
Milestones / Other Key Activities
A | Deployment of application | [27 empty] | X | X | X
B | Test Suite to cover functional testing of all features | [27 empty] | X | X | X
C | Documentation of the application, testing, and usage | [27 empty] | X | X | X
D
E
Minor Tasks: |  |  | 39 | 40 | 41 | 42 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Matthew | Nick | Payton
|  |  | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | 2021-04-11 | 2021-04-18 | 2021-04-25 | 2021-05-02 | 2021-05-09 | 2021-05-16 | 2021-05-23 | 2021-05-30 | 2021-06-06 | 2021-06-13 | 2021-06-20
Version # |  | Change Made: | Project Notes:
Black = Planned Green = Complete Red = Delayed
Formulas:
X = [X]+7